## Overview
	Estimation	Itération 1	Itération 2	Itération 3	Itération 4
Histoire 1	60	78	0	0	0
Histoire 2	65	34	0	0	0
Histoire 3	80	36	0	0	0
Histoire 4	50	0	0	0	0
Histoire 5	50	0	0	0	0
Histoire 6		0	0	0	0
Histoire 7		0	0	0	0
Histoire 8	30	0	0	0	0
Histoire 9		0	0	0	0
Histoire 10		0	0	0	0
Histoire 11		0	0	0	0
Histoire 12		0	0	0	0
Histoire 13		0	0	0	0
Histoire 14		0	0	0	0
Android App	90
Améliorations & Refactoring IT2	100
Améliorations & Refactoring IT3	30
Améliorations & Refactoring IT4	30

	Estimation	Itération 1	Itération 2	Itération 3	Itération 4
	585	147.5	0	0	0

## IT1
				Points restants
HISTOIRE 1					Histoire 1		Histoire 2		Histoire 3		Total
Tâches	Pilote	Copilote	Points réels	Points estimés			Jour	Idéal	Réel	Idéal	Réel	Idéal	Réel	Idéal	Réel
Database design architecture tables and relations	Son	Romain	8	4			0	46	77.5	27	34	27	36	100	147.5
Database requests	Ismael	Youssef	8	4			1	42.7142857142857	77.5	25.0714285714286	33	25.0714285714286	36	92.8571428571429	146.5
OO Design for requests	Romain	Son	10	4			2	39.4285714285714	70	23.1428571428571	25	23.1428571428571	36	85.7142857142857	131
OO Design for requests part 2	Romain	Ismael	10	4			3	36.1428571428571	64	21.2142857142857	20	21.2142857142857	30	78.5714285714286	114
Render List	Tanguy	Son	4	2			4	32.8571428571429	58	19.2857142857143	18	19.2857142857143	24	71.4285714285714	100
Modify list	Mathias	Tanguy	4	2			5	29.5714285714286	50	17.3571428571429	15	17.3571428571429	20	64.2857142857143	85
Combine GUI parts into app	Tanguy	Alexis	8	4			6	26.2857142857143	44	15.4285714285714	12	15.4285714285714	15	57.1428571428571	71
Archive list	Benjamin	Mathias	1.5	2			7	23	40	13.5	12	13.5	14	50	66
Add product	Benjamin	Romain	2	2			8	19.7142857142857	32	11.5714285714286	10	11.5714285714286	14	42.8571428571429	49
Make controllers	Youssef	Ismael	10	8			9	16.4285714285714	25	9.64285714285714	10	9.64285714285714	10	35.7142857142857	45
Add List	Tanguy	Alexis	2	4			10	13.1428571428571	20	7.71428571428572	8	7.71428571428572	8	28.5714285714286	36
Gradle build system	Alexis	Ayoub	8	4			11	9.85714285714286	16	5.78571428571429	8	5.78571428571429	6	21.4285714285714	30
Main controller	Alexis	Ayoub	2	2			12	6.57142857142857	10	3.85714285714286	4	3.85714285714286	4	14.2857142857143	18
				13	3.28571428571429		1.92857142857143		1.92857142857143		7.14285714285715	0
				14	0		0		0		0	0

Total			77.5	46
				14					Note :	Daily time spent on tasks / Where not initialy recored, / Hence this burndown is an approximation

HISTOIRE 2
Tâches	Pilote	Copilote	Points réels	Points estimés
Recipe edition	Tanguy	Ayoub	4	4
Database tables	Son	Romain	5	4
Database requests	Youself	Ismael	10	4
JSON import backend	Benjamin	Mathias	4	4
Display recipe	Ayoub	Tanguy	4	4
JSON import frontend	Ayoub	Mathias	4	4
Main controller	Ayoub	Alexis	2	2
Examples de recettes (population DB)	Alexis	Son	1	1

Total			34	27

HISTOIRE 3
Tâches	Pilote	Copilote	Points réels	Points estimés
Main Menu GUI	Ayoub	Tanguy	1	1
Database tables	Romain	Mathias	4	2
Add/delete recipe per day	Tanguy	Ayoub	4	4
Autocomplete menu	Mathias	Benjamin	2	2
Calendar view	Benjamin	Mathias	5	4
Filters view	Mathias	Benjamin	2	2
Replace unwanted dish/menu	Benjamin	Mathias	2	2
Suggestion menu	Mathias	Benjamin	2	2
Main controller	Ayoub	Alexis	2	2
Database requests	Youssef	Ismael	10	4
Connect DAO and controller for Ingredient	Ayoub	Ismael	2	2
'			36	27

## IT2
				Points restants
HISTOIRE 5					HISTOIRE 5		Améliorations & Refactoring				Total
Tâches	Pilote	Copilote	Points réels	Points estimés			Jour	Idéal	Réel	Idéal	Réel			Idéal	Réel
Map API/LIB recherche	Naoufal	Ismail	4	4			0	45	44.8	92.4	94
Map API implémentation	Ismail	Naoufal	4	4			1	41.7857142857143	44.8	87.2857142857143	92.4			129.071428571429	137.2
Map view recherche sidebar + picture load	Ismail	Naoufal	4	4			2	38.5714285714286	44.8	80.5714285714286	81.4			119.142857142857	126.2
Refractor MAP	Ayoub	Ismail	2	2			3	35.3571428571429	44.8	73.8571428571429	74.4			109.214285714286	119.2
Refractor MAP + Integration Controlleur	Ayoub	Naoufal	2	2			4	32.1428571428571	40.8	67.1428571428571	66.4			99.2857142857143	107.2
Configuration gradle / ajout boutton map menu principal	Ismail	Ayoub	2	2			5	28.9285714285714	36.8	60.4285714285714	60.4			89.3571428571429	97.2
Implémenter bdd base	Naoufal	Ayoub	2	2			6	25.7142857142857	36.8	53.7142857142857	52.4			79.4285714285714	89.2
Controleur map	Ayoub	Ismail	2	2			7	22.5	36.8	47	50.4			69.5	87.2
Implémentation alerte field + MAP	Ismail	Alexis	2	2			8	19.2857142857143	32.8	40.2857142857143	37.4			59.5714285714286	70.2
Implementer bdd Magasin Prix	Naoufal	Youssef	2	2			9	16.0714285714286	30.8	33.5714285714286	49.4			49.6428571428571	80.2
Refactor BDD Magasins Prix	Naoufal	Alexis	1	1			10	12.8571428571429	30.8	26.8571428571429	31.4			39.7142857142857	62.2
Implémenter controller map avec les DAO	Ismail	Alexis	2	2			11	9.64285714285714	30.8	20.1428571428571	31.4			29.7857142857143	62.2
Réparer la partie listener du comboBox address / ajout fxml	Ismail	Naoufal	3	2			12	6.42857142857143	30.8	13.4285714285714	31.4			19.8571428571429	62.2
Shop Ingredient view	Tanguy	Ayoub	1.5	2			13	3.21428571428572	30.8	6.71428571428571	0			9.92857142857142	30.8
Ingredient Price	Tanguy	Son	1	1			14	0	0	0	0			0	0
Bug fix swtich sql	Tanguy	Romain	1.5	2
Ingredient and map	Tanguy	Son	0.8	1		NOTE: not all hours were logged daily, some are hence missing (missing data filled in on day 14)
Fix shop sql request and fix bug mapController / mapview	Ismail	Naoufal	2	2
Populate DB	Youssef	Alexis	2	2
Populate DB shops	Youssef	Matthias	2	2
Debug DB insert shops and ingredient price	Youssef	Matthias	2	2
				3.21428571428571
				6.71428571428571
Total			44.8	45
			Initial estimated total:	50

Améliorations & Refactoring
Tâches	Pilote	Copilote	Points réels	Points estimés
Refactor MainConttroller	Ayoub	Tanguy	1	1
Amélioration + Refactor Controllers View	Ayoub	Tanguy	3	4
Refactor controller/view Ingredient	Benjamin	Matthias	3	2
Refactor controller/view Menus	Matthias	Benjamin	3	4
Génération multiple de menus	Benjamin	Matthias	5	5
Refactoring controller instanciation + exception alert	Alexis	Youssef	2	2
Filtres refactor 1	Romain	Benjamin	4	4
Filtres refactor 2	Romain	Son	6	4
DAO refactoring	Benjamin	Romain	4	4
Generalisation DAO	Son	Romain	4	4
Refactor controllers	Son	Romain	4	4
Refactor DTO to model	Benjamin	Romain	2	2
DAO refactoring 2	Romain	Benjamin	4	4
Refactor controllers parametric	Benjamin	Son	4	4
Remplir la db	Youssef	Alexis	2	2
Building and arcgis runtime with gradle	Alexis	Ayoub	2	2
Quick fix alertable refactoring	Alexis		1	1
MapViewController refactoring	Alexis	Naoufal	2	2
Model creation	Romain	Benjamin	4	4
Filtres archive	Romain	Son	4	4
Menus clickable	Matthias	Benjamin	4	4
Added business logic and tests	Alexis		4	4
Upgrade view shopping list	Ayoub	Tanguy	1.3	2
Test table view	Ayoub	Tanguy	1.5	2
Update shopping list	Ayoub	Tanguy	2.6	3
Add shopping list + fix db	Ayoub	Tanguy	4	4
Fix bug recipe and shopping list	Ayoub	Tanguy	1.5	2
Upgrade instruction view	Tanguy	Ayoub	0.5	1
Upgrade recipe view	Tanguy	Ayoub	2	2
Bug fix	Tanguy	Romain	1	1
Ingredient Recipe FX	Tanguy	Son	2	2
Ingredient Recipe FX 2	Tanguy	Son	2	2
Maintaining burndown	Alexis		2	2

Total			92.4	94
			Initial estimated total:	100

## IT2_Hour_Log
Tâches	Jour 1	Jour 2	Jour 3	Jour 4	Jour 5	Jour 6	Jour 7	Jour 8	Jour 9	Jour 10	Jour 11	Jour 12	Jour 13	Jour 14	PILOTE :	COPILOTE :
HISTOIRE 5
Map API/LIB recherche														4	Naoufal	Ismail
Map API implémentation				4											Ismail	Naoufal
Map view recherche sidebar + picture load					4										Ismail	Naoufal
Refractor MAP								2							Ayoub	Ismail
Refractor MAP + Integration Controlleur														2	Ayoub	Naoufal
Configuration gradle / ajout boutton map menu principal								2							Ismail	Ayoub
Implémenter bdd base														2	Naoufal	Ayoub
Controleur map									2						Ayoub	Ismail
Implémentation alerte field + MAP														2	Ismail	Alexis
Implementer bdd Magasin Prix														2	0	0
Refactor BDD Magasins Prix														1	0	0
Implémenter controller map avec les DAO														2	0	0
Réparer la partie listener du comboBox address / ajout fxml														3	0	0
Shop Ingredient view														1.5	0	0
Ingredient Price														1	0	0
Bug fix swtich sql														1.5	0	0
Ingredient and map														0.8	0	0
Fix shop sql request and fix bug mapController / mapview														2	0	0
Populate DB														2	0	0
Populate DB shops														2	0	0
Debug DB insert shops and ingredient price														2	0	0
0															0	0
0
Total
0
0
NOTE: not all hours were logged daily, some are hence missing from this page (missing data filled in on day 14)
SUMS :	0	0	0	4	4	0	0	4	2	0	0	0	0	30.8
Améliorations & Refactoring
Refactor MainConttroller														1	Ayoub	Tanguy
Amélioration + Refactor Controllers View														3	Ayoub	Tanguy
Refactor controller/view Ingredient		2													Alexis	Youssef
Refactor controller/view Menus		4													Romain	Son
Génération multiple de menus				4	2										Benjamin	Romain
Refactoring controller instanciation + exception alert			4		4										Son	Romain
Filtres refactor 1														4	Son	Romain
Filtres refactor 2						4									Benjamin	Romain
DAO refactoring														2	Romain	Benjamin
Generalisation DAO				4											Benjamin	Son
Refactor controllers						4									0	0
Refactor DTO to model														5	Benjamin	Matthias
DAO refactoring 2		3													Benjamin	Matthias
Refactor controllers parametric			3												Matthias	Benjamin
Remplir la db		2													Youssef	Alexis
Building and arcgis runtime with gradle							2								0	0
Quick fix alertable refactoring								1							0	0
MapViewController refactoring									2						0	0
Model creation									4						0	0
Filtres archive										4					0	0
Menus clickable										2	2				Matthias	Benjamin
Added business logic and tests											4
Upgrade view shopping list														1.3
Test table view
Update shopping list														2.6
Add shopping list + fix db														4
Fix bug recipe and shopping list														1.5
Upgrade instruction view														2
Upgrade recipe view														2
Bug fix														1
Maintaining burndown														2
0
0
0
0
0
0
0
0
SUMS :	0	11	7	8	6	8	2	1	6	6	6	0	0	31.4

## IT3
				Points restants
HISTOIRE 4					HISTOIRE 4		Améliorations & Refactoring		HISTOIRE 8		Total
Tâches	Pilote	Copilote	Points réels	Points estimés			Jour	Idéal	Réel	Idéal	Réel	Idéal	Réel	Idéal	Réel
Verify email address	Ayoub	Tanguy	0.2	0.2			0	25.7	19.7	57.35	65	28	28
Button export pdf design	Benjamin	Tanguy	0.2	0.2			1	23.8642857142857	19.7	60.3571428571429	53.35	26	25.5	110.221428571429	98.55
Export de PDF	Benjamin	Son	5	5			2	22.0285714285714	18.7	55.7142857142857	51.85	24	25.5	101.742857142857	96.05
Save before export	Tanguy	Benjamin	0.3	0.3			3	20.1928571428571	17.5	51.0714285714286	49.25	22	21.5	93.2642857142857	88.25
Email sending api	Son	Romain	2	2			4	18.3571428571429	14.2	46.4285714285714	46.15	20	21.5	84.7857142857143	81.85
Email sending api	Romain	Son	1	1			5	16.5214285714286	14	41.7857142857143	36.35	18	21.5	76.3071428571429	71.85
Email with attachment	Matthias	Romain	1	2			6	14.6857142857143	14	37.1428571428571	36.35	16	21.5	67.8285714285714	71.85
Email testing	Son	Romain	2	2			7	12.85	14	32.5	32.1	14	21.5	59.35	67.6
lib javamail Doc	Ayoub	Son	1	2			8	11.0142857142857	14	27.8571428571429	28.6	12	21.5	50.8714285714286	64.1
Ajout vue send email + controller associé	Ayoub	Son	1	2			9	9.17857142857143	14	23.2142857142857	20.7	10	21.5	42.3928571428571	56.2
Maj Email Style	Ayoub	Tanguy	2	2			10	7.34285714285714	14	18.5714285714286	18.3	8	21.5	33.9142857142857	53.8
Amélioration Code Email	Ayoub	Tanguy	1	2			11	5.50714285714286	14	13.9285714285714	17	6	21.5	25.4357142857143	52.5
Ajout fonctionnalité send email	Ayoub	Son	2	4			12	3.67142857142857	14	9.28571428571428	16.2	4	21.5	16.9571428571428	51.7
fix pdf + email jar	Ayoub	Son	1	1			13	1.83571428571429	14	4.64285714285714	16.2	2	21.5	8.47857142857142	51.7
				14	0	0	0	7.2	0	0	0	7.2

				NOTE: IF not all hours are logged daily, missing data will be filled in on day 14

				1.83571428571429
				4.64285714285714
Total			19.7	25.7		2
			Initial estimated total:	50

Améliorations & Refactoring
Tâches	Pilote	Copilote	Points réels	Points estimés
Exceptions refactoring	Alexis	Naoufal	2	2
Exceptions refactoring 2	Alexis	Naoufal	1	1
Menu generation coherence in case of exception	Alexis	Matthias	0.25	1
Refactor MenusController	Benjamin	Tanguy	2	2
Refactor Recipe Controller	Tanguy	Benjamin	2	2
Refactor ShoppingList Controller	Tanguy	Benjamin	4	4
New JsonImport	Naoufal	Youssef	4	4
Refactor PopulateDB	Naoufal	Youssef	2	2
Multiple recipe import	Naoufal	Youssef	2	2
Create menu text fields	Tanguy	Matthias	1.5	1.5
Fix menu save	Tanguy	Matthias	0.5	0.5
Fix menu save 2	Tanguy	Benjamin	0.3	0.3
Difference between add and modify recipe	Tanguy	Benjamin	0.8	0.8
Upgrade ShoppingList 1 and 2 (two tasks)	Tanguy	Benjamin	1.2	1.2
Fix delete shopping list	Tanguy	Ayoub	0.2	0.2
Import menu in current list	Tanguy	Alexis	0.3	0.3
Make generate menu disableable	Tanguy	Benjamin	0.3	0.3
Upgrade generateMenu view	Tanguy	Benjamin	0.1	0.1
Add export menu	Tanguy	Benjamin	0.3	0.3
Typing tableview/tablecolumn	Tanguy	Benjamin	0.3	0.3
Upgrade map view	Tanguy	Benjamin	0.4	0.4
Fix spinner	Tanguy	Son	1.3	2
Import menu button	Ayoub	Tanguy	2	2
Add ingredient + test	Ayoub	Tanguy	1.5	1.5
Fix import menu	Ayoub	Tanguy	0.3	0.3
Update controller and planning	Benjamin	Tanguy	0.8	8
Fix warning 1 and 2 (two tasks)	Alexis	Tanguy	1.5	1.5
Refactor tests	Alexis	Tanguy	0.5	0.5
Avoid double item in shopping list	Ayoub	Tanguy	1.2	1.2
Upgrade updateToView code	Ayoub	Tanguy	0.5	0.5
Fix price bug	Ayoub	Tanguy	0.8	0.8
Fix shopping list double bug	Tanguy	Benjamin	1	1
Fix bug + prepare demo	Benjamin	Tanguy	0.5	0.5
Code quality and fix warnings	Alexis	Romain	4	4
Refactor exceptions	Romain	Son	2	2
Code refactoring	Romain	Son	2	2
Burndown maintenance	Alexis		2	1
Ajout méthode conversion Menu vers ShoppingList	Ayoub	Romain	1	1
Ajout tests méthode conversion Menu Vers ShoppingList	Ayoub	Benjamin	1	1
Add recipe cooking style	Youssef	Matthias	2	2
Add recipe type	Youssef	Matthias	2	2
Add recipe	Youssef	Naoufal	2	2
Test importJson	Youssef	Matthias	2	2

Total			57.35	65
			Initial estimated total:	30

HISTOIRE 8
Tâches	Pilote	Copilote	Points réels	Points estimés
Research shortests paths	Ismail	Matthias	2	2
Home address for map	Alexis	Ismail	2	2
Home address for map 2	Alexis	Ismail	2	2
Add button find the shortests path	Ismail	Naoufal	0.5	0.5
Error management , bug correction	Ismail	Naoufal	2	2
Create Model Map	Naoufal	Alexis	2	2
Refactor map and add shortest path button	Ismail	Naoufal	4	4
mapViewController delete thread cannot use path	Ismail	Matthias	2	2
Add shortests path with travel mode	Ismail	Youssef	4	4
Bug correction shortests path	Naoufal	Ismail	4	4
Delete and split useless path method	Ismail	Youssef	2	2
Upgrade map view	Tanguy	Ayoub	0.5	0.5
fix route jar	Ayoub	Ismail	1	1

Total			28	28
			Initial estimated total:	30

## IT3_Hour_Log
Tâches	Jour 1	Jour 2	Jour 3	Jour 4	Jour 5	Jour 6	Jour 7	Jour 8	Jour 9	Jour 10	Jour 11	Jour 12	Jour 13	Jour 14	PILOTE :	COPILOTE :
HISTOIRE 4
Verify email address					0.2										Alexis	Ismail
Button export pdf design			0.2												Alexis	Ismail
Export de PDF		1	1	3											Benjamin	Son
Save before export				0.3											Tanguy	Benjamin
Email sending api														2	Son	Romain
Email sending api														1	Romain	Son
Email with attachment														1	Matthias	Romain
Email testing														2	Son	Romain
lib javamail Doc														1	Ayoub	Son
Ajout vue send email + controller associé														1	Ayoub	Son
Maj Email Style														2	Ayoub	Tanguy
Amélioration Code Email														1	Ayoub	Tanguy
Ajout fonctionnalité send email														2	Ayoub	Son
fix pdf + email jar														1	Ayoub	Son
0															0	0
0															0	0
0															0	0
0															0	0
0															0	0
0															0	0
0															0	0
0															0	0
0															0	0
Total

NOTE: IF not all hours are logged daily, missing data will be filled in on day 14
SUMS :	0	1	1.2	3.3	0.2	0	0	0	0	0	0	0	0	14
Améliorations & Refactoring
Exceptions refactoring					2										Alexis	Naoufal
Exceptions refactoring 2					4										Alexis	Naoufal
Menu generation coherence in case of exception							0.25								Alexis	Matthias
Refactor MenusController							2								Benjamin	Tanguy
Refactor Recipe Controller								2							Tanguy	Benjamin
Refactor MenusController	2														Benjamin	Tanguy
Refactor Recipe/ShoppingList Controller				1	3				2						Tanguy	Benjamin
Refactor PopulateDB														2	Naoufal	Youssef
Multiple recipe import														2	Naoufal	Youssef
Create menu text fields			1.5												Tanguy	Matthias
Fix menu save			0.5												Tanguy	Matthias
Fix menu save 2			0.3												Tanguy	Benjamin
Difference between add and modify recipe				0.3											Tanguy	Benjamin
Upgrade ShoppingList 1 and 2 (two tasks)				1.2											Tanguy	Benjamin
Fix delete shopping list				0.3											Tanguy	Ayoub
Import menu in current list				0.3											Tanguy	Alexis
Make generate menu disableable								0.3							Tanguy	Benjamin
Upgrade generateMenu view								0.1							Tanguy	Benjamin
Add export menu								0.3							Tanguy	Benjamin
Typing tableview/tablecolumn								0.8							Tanguy	Benjamin
Upgrade map view									0.3						Tanguy	Benjamin
Fix spinner										0.4					Tanguy	Son
Import menu button	2										1.3				0	0
Add ingredient + test		1.5
Fix import menu			0.3													Tanguy
Update controller and planning					0.8											Tanguy
Fix warning 1 and 2 (two tasks)									1.5							Tanguy
Refactor tests									0.5							Tanguy
Avoid double item in shopping list									1.2
Upgrade updateToView code									0.4
Fix price bug												0.8
Fix shopping list double bug
Fix bug + prepare demo									2	2
Code quality and fix warnings
Refactor exceptions							2
Code refactoring														2
Burndown maintenance														2
Ajout méthode conversion Menu vers ShoppingList														1
Ajout tests méthode conversion Menu Vers ShoppingList														1
Add recipe cooking style														2
Add recipe type														2
Add recipe														2
Test importJson														2
SUMS :	4	1.5	2.6	3.1	9.8	0	4.25	3.5	7.9	2.4	1.3	0.8	0	9

HISTOIRE 8
Research shortests paths			2													2
Home address for map	2															2
Home address for map 2			2													2
Add button find the shortests path														0.5		0.5
Error management , bug correction														2		2
Create Model Map														2		2
Refactor map and add shortest path button														4		4
mapViewController delete thread cannot use path														2		2
Add shortests path with travel mode														4		4
Bug correction shortests path														4		4
Delete and split useless path method														2		2
Upgrade map view	0.5															0.5
fix route jar														1		1
0																0
0																0
0																0
0																0
0																0
0																0
0																0
0																0
0																0
0																0
Total
SUMS:	2.5	0	4	0	0	0	0	0	0	0	0	0	0	21.5

## IT4
				Points restants
Améliorations & Refactoring					Améliorations & Refactoring		Android App		Total
Tâches	Pilote	Copilote	Points réels	Points estimés			Jour			Idéal	Réel	Idéal	Réel	Idéal	Réel
Adding pictures	Son	Tanguy	1	2			0			37.7	42.3	77	77
Adding pictures 2	Son	Ben	2	2			1			39.2785714285714	33.6	73.3571428571429	74	112.635714285714	107.6
Warnings and code quality	Alexis	Matthias	2	2			2			36.2571428571429	26.8	67.7142857142857	70	103.971428571429	96.8
Method refactoring	Alexis	Matthias	1	1			3			33.2357142857143	26.6	62.0714285714286	68	95.3071428571429	94.6
Recipe images	Ben	Son	3	4			4			30.2142857142857	25.6	56.4285714285714	59	86.6428571428571	84.6
Recipe images 2	Ben	Tanguy	2	2			5			27.1928571428571	23.6	50.7857142857143	48	77.9785714285714	71.6
Bug fixing	Ben		2	2			6			24.1714285714286	18.6	45.1428571428571	39	69.3142857142857	57.6
Refactoring	Ben	Romain	2	2			7			21.15	16.6	39.5	27	60.65	43.6
Client notes	Ben	Tanguy	3	4			8			18.1285714285714	8.8	33.8571428571429	18	51.9857142857143	26.8
Travel modes en français	Ben	Tanguy	0.2	0.2			9			15.1071428571429	8.8	28.2142857142857	10	43.3214285714286	18.8
Amelioration vue CreateMenu	Tanguy	Ben	0.5	0.5			10			12.0857142857143	8	22.5714285714286	9	34.6571428571429	17
Amelioration vue DisplayMenu	Tanguy	Ben	0.2	0.2			11			9.06428571428571	8	16.9285714285714	7	25.9928571428571	15
Amelioration vue GenerateMenu	Tanguy	Ben	0.2	0.2			12			6.04285714285714	8	11.2857142857143	3	17.3285714285714	11
Amelioration CSS	Tanguy	Ayoub	1	1			13			3.02142857142857	6	5.64285714285714	1	8.66428571428571	7
Amelioration CSS	Tanguy	Ayoub	2	2			14			0	0	0	0	0	0
Amelioration CSS	Tanguy	Ayoub	0.8	1
Amelioration CSS	Tanguy	Ayoub	1	1		NOTE: IF not all hours are logged daily, missing data will be filled in on day 14
Amelioration CSS Spinner/TableView	Tanguy	Son	0.2	0.2					Note: order of tasks here is not the order they were performed in
Amelioration vue Menu	Tanguy	Ben	1	1
Amelioration vue Menu	Tanguy	Ben	1	1
Amelioration vue Display Menu FXML	Tanguy	Ben	0.8	1
Ajout upload images	Tanguy	Son	1.5	2		#REF!
Ajout image dans display	Tanguy	Son	0.5	1		3.02142857142857
Ajout sauvegarde image	Tanguy	Ben	0.8	1		5.64285714285714
Populate DB	Youssef	Matthias	2	2
Populate DB	Youssef	Alexis	2	2
DAO test update	Youssef		2	2
Model refactoring	Romain	Alexis	2	2

Total			37.7	42.3
			Initial estimated total:	30

Android App
Tâches	Pilote	Copilote	Points réels	Points estimés
App prototyping	Ayoub	Son	4	4
ShoppingList export json/QR code	Ben	Romain	1	2
QR code optimizations	Ben	Romain	3	4
App android re-design	Ayoub	Tanguy	1	1
Android app fragments	Ayoub	Tanguy	6	4
Recherche docoumentation anrdoid	Ismail	Ayoub	2	2
Ajout fontionnalité de base pour la phase structure	Ismail	Ayoub	4	4
Documentation stockage SQLite android	Alexis	Ismail	2	2
Implementation SQLite	Naoufal	Ismail	2	2
Fonctionnalité de stockage format json	Son	Alexis	2	2
Ajout checkbox ingredient	Ayoub	Son	1	1
Ajout des ingredients pour fonctionnalité cochage	Ismail	Ayoub	2	2
Ajout partie type ingrdient	Ayoub	Naoufal	4	4
Fontionnalité scan QR code json	Ayoub	Son	1	2
Phase de test of app on phone	Ismail	Ayoub	1	1
Correction bug version build graddle	Ismail	Naoufal	4	4
Correction bug info recette	Ayoub	Ben	1	1
Correction bug suppression shopping list	Ayoub	Tanguy	1	1
Ajout vue ingredient	Ayoub	Ismail	2	2
Amelioration vue ingredient v1	Tanguy	Ayoub	1	1
Amelioration app design part 1	Naoufal	Youssef	3	3
Refactor model et suppression	Naoufal	Youssef	4	4
Ajout header dans la vue ingredient	Son	Ayoub	2	2
Implementation prototype	Son	Ayoub	2	2
Amelioration design liste de courses	Tanguy	Ayoub	2	2
Ajout fontionnalité séléction	Ismail	Tanguy	2	2
Amerlioration vue selection	Ismail	Tanguy	2	2
Implementation prototype selection	Romain	Tanguy	2	2
Amerioration vue shopping list	Son	Tanguy	2	2
Amerioration vue shopping list v2	Son	Ismail	2	2
Ajout class imbriqué ViewHolder	Romain	Ismail	2	2
Test application + correction bug	Naoufal	Tanguy	2	2
Modification private class imbriqué	Alexis	Tanguy	2	2
Interface communication vue ingredient	Ayoub	Matthias	2	2
Save list state	Romain	Ayoub	1	2

Total			77	79
			Initial estimated total:	90

## IT4_Hour_Log
	Day 1	Day 2	Day 3	Day 4	Day 5	Day 6	Day 7	Day 8	Day 9	Day 10	Day 11	Day 12	Day 13	Day 14
Améliorations & Refactoring
Adding pictures				1											Son	Tanguy
Adding pictures 2					2										Son	Ben
Warnings and code quality						2									Alexis	Matthias
Method refactoring						1									Alexis	Matthias
Recipe images								3							Ben	Son
Recipe images 2								2							Ben	Tanguy
Bug fixing							2								Ben	0
Refactoring		2													Ben	Romain
Client notes		3													Ben	Tanguy
Travel modes en français	0.2														Ben	Tanguy
Amelioration vue CreateMenu	0.5														Tanguy	Ben
Amelioration vue DisplayMenu	0.2														Tanguy	Ben
Amelioration vue GenerateMenu	0.2														Tanguy	Ben
Amelioration CSS	1														Tanguy	Ayoub
Amelioration CSS	2														Tanguy	Ayoub
Amelioration CSS		0.8													Tanguy	Ayoub
Amelioration CSS		1													Tanguy	Ayoub
Amelioration CSS Spinner/TableView			0.2												Tanguy	Son
Amelioration vue Menu						1									Tanguy	Ben
Amelioration vue Menu						1									Tanguy	Ben
Amelioration vue Display Menu FXML								0.8							Tanguy	Ben
Ajout upload images								1.5							Tanguy	Son
Ajout image dans display								0.5							Tanguy	Son
Ajout sauvegarde image										0.8					Tanguy	Ben
Populate DB														2	Youssef	Matthias
Populate DB														2	Youssef	Alexis
DAO test update														2	Youssef	0
Model refactoring													2		Romain	Alexis
0															0	0
0															0	0
0															0	0
0															0	0
0															0	0
0															0	0
0															0	0
0															0	0
0															0	0
0															0	0
0															0	0
0															0	0
0															0	0
0															0	0
0															0	0
SUMS :	4.1	6.8	0.2	1	2	5	2	7.8	0	0.8	0	0	2	6

App prototyping		4													Ayoub	Son
ShoppingList export json/QR code	1														Ben	Romain
QR code optimizations					3										Ben	Romain
App android re-design										1					Ayoub	Tanguy
Android app fragments								6							Ayoub	Tanguy
Recherche docoumentation anrdoid	2														Ismail	Ayoub
Ajout fontionnalité de base pour la phase structure				4											Ismail	Ayoub
Documentation stockage SQLite android			2												Alexis	Ismail
Implementation SQLite				2											Naoufal	Ismail
Fonctionnalité de stockage format json					2										Son	Alexis
Ajout checkbox ingredient						1									Ayoub	Son
Ajout des ingredients pour fonctionnalité cochage						2									Ismail	Ayoub
Ajout partie type ingrdient							4								Ayoub	Naoufal
Fontionnalité scan QR code json				1											Ayoub	Son
Phase de test of app on phone								1							Ismail	Ayoub
Correction bug version build graddle						4									Ismail	Naoufal
Correction bug info recette						1									Ayoub	Ben
Correction bug suppression shopping list						1									Ayoub	Tanguy
Ajout vue ingredient				2											Ayoub	Ismail
Amelioration vue ingredient v1							1								Tanguy	Ayoub
Amelioration app design part 1							3								Naoufal	Youssef
Refactor model et suppression									4						Naoufal	Youssef
Ajout header dans la vue ingredient									2						Son	Ayoub
Implementation prototype					2										0	0
Amelioration design liste de courses							2
Ajout fontionnalité séléction					2
Amerlioration vue selection							2
Implementation prototype selection					2
Amerioration vue shopping list									2
Amerioration vue shopping list v2											2
Ajout class imbriqué ViewHolder												2
Test application + correction bug													2
Modification private class imbriqué												2
Interface communication vue ingredient								2
Save list state														1
0
0
0
0
0
0
0
0
0
0
0
0
0
Total

SUMS:	3	4	2	9	11	9	12	9	8	1	2	4	2	1